## Sheet2
Planned
WIP
Completion status
Review Status
| Week Start Date | 2024-09-21 | 2024-09-28 | 2024-10-05 | 2024-10-12 | 2024-10-19 | 2024-10-26 | 2024-11-02 | 2024-11-09 | 2024-11-16 | 2024-11-23 | 2024-11-30 | 2024-12-07 | 2024-12-14 | 2025-01-04 | 2025-01-11
| Week End Date | 2024-09-27 | 2024-10-04 | 2024-10-11 | 2024-10-18 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 2024-11-15 | 2024-11-22 | 2024-11-29 | 2024-12-06 | 2024-12-13 | 2024-12-20 | 2025-01-10 | 2025-01-17
| Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Chapter # | Chapter Description
1 | Introduction to Generative AI | 2024-10-04: 1/ Grammer 2/ Content 3/ AI 4/ Pictures/ Figures 5/ Format 6/ plagiarism o Understanding Generative AI o Importance and Applications o The Infinite Potential of Generative AI for the Future o Summary
2 | Generative AI with AWS | 2024-10-11: 1/ Grammer 2/ Content 3/ AI 4/ Pictures/ Figures 5/ Format 6/ plagiarism
3 | Introduction to Amazon Bedrock | 2024-10-18: 1/ Grammer 2/ Content 3/ AI 4/ Pictures/ Figures 5/ Format 6/ plagiarism
4 | Overview of Prompt Engineering & In-Context Learning | 2024-10-25: 1/ Grammer 2/ Content 3/ AI 4/ Pictures/ Figures 5/ Format 6/ plagiarism
5 | Overview of Use Cases in This Book | bar: 2025-01-17
6 | Overview of Retrieval-Augmented Generation (RAG) | 2024-09-27: 1/ Grammer 2/ Content 3/ AI 4/ Pictures/ Figures 5/ Format 6/ plagiarism
7 | Overview of Amazon Bedrock Knowledge Base | 2024-09-27: 1/ Grammer 2/ Content 3/ AI 4/ Pictures/ Figures 5/ Format 6/ plagiarism
8 | Overview of Safeguard's Practice | 2024-10-04: 1. Overview of Safeguard's Practice o Introduction to Responsible AI o Why Responsible AI is Important o Introduction to Amazon Bedrock Guardrails o Sample Application: Building Amazon Bedrock Guardrails o Introduction to Watermark Detection o Understanding the Importance of Watermark Detection o Governance & Monitoring o Summary
9 | Overview of Amazon Bedrock Agents | bar: 2024-10-11
10 | Overview of Model Customization | bar: 2024-10-18
11 | Overview of Model Evaluation | bar: 2024-10-25
12 | Overview of Best Model Selection and Best Practices | bar: 2024-11-01
13 | Overview of Security and Privacy of Amazon Bedrock | bar: 2024-11-08
14 | Overview of GenAIOps | bar: 2024-11-15
15 | Overview of Prompt Management | bar: 2024-11-22
16 | Overview of Prompt Flow | bar: 2024-11-29
17 | Overview of Amazon Bedrock studio | bar: 2024-12-06
18 | Overview of Provisional Throughput | bar: 2024-12-13
19 | Overview of Multimodal Capability | bar: 2024-12-20
20 | Conclusion | bar: 2025-01-10
21 | Appendix | bar: 2025-01-17